## Schedule
Device/Equipment Borrowing System
|  | July | [30 empty] | August | [30 empty] | September | [29 empty] | October
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Database | Spec
Report Spec | bar: July 18; August 11 to August 15
Build up | bar: July 18
Maintain | Equipment | bar: July 21
Device | bar: July 21
Project | bar: July 21
Person | bar: July 21
Demo/modify | bar: July 21 to July 22
Borrowing Mangement | Equipment | bar: July 23 to July 25; July 28 to August 1; August 4 to August 5
Demo/modify | bar: August 6 to August 8
Device | bar: August 11 to August 15; August 18
Demo/modify | bar: August 19 to August 21
Reminder | E-mail | bar: September 2 to September 5; September 9 to September 12
Websystem | bar: August 22; August 25 to August 29; September 1
Report | Device - usage/free | bar: September 15 to September 17
Equipment - usage/free | bar: September 18 to September 19; September 22
Equipment - Project cost | bar: September 23 to September 26; September 29 to September 30
Demo/modify | bar: October 1 to October 3
Trial-run | Key user | bar: October 6 to October 9
Phase in | Build up environment | bar: October 6 to October 9
Training | bar: October 13
On-line | bar: October 14 to October 17
Note on B17: When user login system, system will remind which task needs to check.
Note on B18: Summary the usage/free situation of device.
Note on B19: Summary the usage/free situation of equipment.
Note on B20: Calculate the usage cost of equipment for project.

## Progress
Date: 8/19
| Task item | status | rate of progress | Comment
Database | Spec | Done | 100%
| Report Spec | Working | 1% | Report format doesn't be defined yet.
| Build up | Done | 100%
Maintain | Equipment | Done | 100%
| Device | Done | 100%
| Project | Done | 100%
| Person | Done | 100%
| Demo/modify | Done | 100%
Borrowing Mangement | Equipment | Done | 100%
| Demo/modify | No status
| Device | Done | 100%
| Demo/modify | No status
Reminder | E-mail | Working | 30%
| Websystem | Working | 50%
Report | Device - usage/free | No status
| Equipment - usage/free | No status
| Equipment - Project cost | No status
| Demo/modify | No status
Trial-run | Key user | No status
Phase in | Build up environment | No status
| Training | No status
| On-line | No status
Note on B16: When user login system, system will remind which task needs to check.
Note on B17: Summary the usage/free situation of device.
Note on B18: Summary the usage/free situation of equipment.
Note on B19: Calculate the usage cost of equipment for project.